## SCRR Job Import Template
id | projectName | clientRef | phase | phaseName | statusType | statusLabel | eta | completionRate
S2670 | Chevallum Industrial Park Phase 2 - Main Switchboard 1600A | Apex Electrical Contracting Pty Ltd | 4 | AS/NZS 61439 QA & Dielectric Testing | amber | Factory Testing & QA Verification | Dispatched in 48 Hours | 80%
S2540 | Regional Pumping Station Upgrade - 400A Weatherproof Control Assembly | Coastline Water & Civil Infrastructure | 5 | FAT Certified & Dispatched / Ready for Delivery | green | Ready for Collection & Freight Staging | Ready for Immediate Dispatch | 100%
S2710 | Maroochydore Commercial Complex - Energex 630A CT Metering Suite | Q-Elec Industrial Contractors | 2 | CNC Laser Cutting & Metal Fabrication | blue | Active Enclosure Fabrication | 6 Business Days | 40%
S2895 | Kawana Health & Specialist Suites - Distribution Boards (x4 Units) | ProActive Power & Energy Solutions | 1 | CAD Schematics & Engineering Approval | blue | Engineering Submittal Approved | 10 Business Days | 20%
S3010 | Sunshine Coast Solar Farm - Modular Outdoor Switchgear Array | Pacific Renewable Grid Services | 3 | Copper Busbar Looming & Component Wiring | amber | Active Busbar Assembly | 4 Business Days | 60%